| Task | When? | Note |
| --- | --- | --- |
| Carefully run 2_manual_qc_and_config.ipynb for 3 good participants: channel + IC selection | 13. – 17.7. | 2 h |
| Run 3_preprocessing.ipynb for the batch of 3 participants | 13. – 17.7. | 0.5 h |
| Run 4_averaging.ipynb for the batch of 3 participants to ensure integrity of pipeline from start-to-finish | 13. – 17.7. | 0.5 h |
| Carefully run 2_manual_qc_and_config.ipynb for 17 remaining good participants | 20. – 24.7. | 4 |
| Fix 1_bids_conversion: EOG magnitude needs to be corrected | 20. – 24.7. | 1 |
| Re-run 1_bids_conversion for one participant & check potential influence on ICA (find_bads_eog) | 20. – 24.7. | 0.5 |
| Re-run 1_bids_conversion for all participants | 20. – 24.7. | 0.5 |
| Double-check code in 3_preprocessing.ipynb and write detailed, low-level comments | 20. – 24.7. | 2 h |
| Run 3_preprocessing.ipynb for all 19 participants | 20. – 24.7. | 1 h |
| Communication team: - Sharing what I have (Notebooks 1,2, 3 + preprocess_config.csv for IDs > 19) - Necessity of adjustments in data curation for merging This is what I promised to do before SEPEX! Explain how output of 3_preprocessing.ipynb can be used, offer video call appointment after vacation to explain preprocessing pipeline, share DRAFT of 4_averaging.ipynb. | 20. – 24.7. | 3h |
| Run 4_averaging.ipynb just out of curiosity | 20. – 24.7. | 0,5 h |
| Adjust and comment 4_averaging.ipynb: plotting, testing, understanding | After vacation | 3.5 h |
| Run final 4_averaging.ipynb with 19 participants | After vacation | 2h (runtime) |
| Share final script 4_averaging.ipynb and preliminary results | After vacation | 2h |
| Run the pipeline for remaining subjects | Dependency team | 3h |
| Classifier analysis | Far future? |  |
| Thesis multivariate analysis | Far future? |  |

Meeting with Laura:

- Show subjects_processing_stage.xlsx

  - Walk through the table… later: we’ll have a closer look at data curation

- Walk through notebooks 1 to 3 briefly

- Show averaging results

- What I will share:

  - Preprocessed data

  - Notebooks 1 to 3

    - Did not manage to fully comment Notebook 3

  - Configuration file